## Status
RIVA128 to do:
Task
Class 001 methods | The beta factor is not used
Class 002 methods | Seems fine, ALWAYS CHECK FOR BUGS
Class 003 methods | The chroma key set is not tested
Class 004 methods | NONE
Class 005 methods | NONE
Class 006 methods | Seems fine, ALWAYS CHECK FOR BUGS
Class 007 methods | Seems fine, ALWAYS CHECK FOR BUGS
Class 008 methods | NONE
Class 009 methods | NONE
Class 00a methods | NONE
Class 00b methods | NONE
Class 00c methods | NONE
Class 00d methods | NONE
Class 00e methods | NONE
Class 010 methods | It does at least partially work, but some junk gets sent to the top of the screen
Class 011 methods | Seems fine, ALWAYS CHECK FOR BUGS
Class 012 methods | NONE
Class 014 methods | NONE
Class 015 methods | NONE
Class 017 methods | NONE
Class 018 methods | NONE
Class 01c methods | Maybe done, verify!
Runout | Seems fine, ALWAYS CHECK FOR BUGS
Fix remaining FIFO bugs | Some fixed, there are probably still bugs
DMA Engine
Mediaport
3D Core (TODO: Research)
Notifier Engine | Hardware works, software untested
Cleanup code
Dumb Framebuffer (DFB)
Cursor (RAMDAC_CU) | There is special hardware support, but it just renders anyway using Class 011? At least emulate starting pos
Chroma Key | In progress
Pattern | In progress
Unify position/size structs
Code cleanup

## Bugs
Bugs - last updated 24 March 2025 | Status
"1000Hz" in VESA text mode
1280x1024x16bpp and higher fucked up (wrong resolution set, totally wrong rendering)
8bpp doesn't do crap
VESA: Mode X is broken (DOOM, Boulderoid)
VESA: DOOM is broken
Windows 9x: card not detected
32bpp BSOD on windows 2000
Windows XP Failures
Random Blits end up in the middle of the screen?!
AGP broken
ZX broken
Sometimes there are spurious rectangles at 90 degrees to the valid ones (WHAT???)
GDI-D: "Active Desktop Recovery" text screwed up

## Resolution
Resolution Testing - RIVA 128 (very very early v0.6) | Resolution | Bitdepth | Result (Win2000) | Result (WinXP)
| 640x480 | 8 | NOT WORKING
| 800x600 | 8 | NOT WORKING
| 640x480 | 16 | WORKING (as much as is implemented)
| 800x600 | 16 | WORKING (as much as is implemented)
| 1024x768 | 16 | WORKING (as much as is implemented)
| 1152x864 | 16 | WORKING (as much as is implemented)
| 1280x1024 | 16 | SORTA WORKING (very screwed up rendering)
| 1600x1200 | 16 | BSOD nv3_mini+0x164c3
| 640x480 | 32 | BSOD win32k+13c692 (CHECK CALLSTACK)
| 800x600 | 32 | BSOD win32k+13c692 (CHECK CALLSTACK)
| 1024x768 | 32 | BSOD win32k+13c692 (CHECK CALLSTACK) | WORKING (as much as is implemented)
| 1152x864 | 32 | BSOD win32k+13c692 (CHECK CALLSTACK)

## Bus
Bus Testing - last updated 22 March 2025 | Bus | Result
| PCI | WORKING
| AGP | NOT WORKING

## App Compatibility - VESA
VESA Compatibility Testing - last updated 22 March 2025 | Result
Boulderoid v1.15 | Screwed up rendering (unrecognisable)
DOOM | Screwed up rendering (recognisable)
Epic Pinball | NOTHING
Jazz Jackrabbit | MOSTLY GOOD
Skyroads | GOOD
Tyrian | Screwed up rendering (recognisable)
Terminal Velocity | GOOD (very slow)
Duke Nukem 3D | GOOD (very slow)
Windows XP | Screwed up rendering (KINDA recognisable)